Java Track – Day 4 Assignment

Mavericks Segue 2026   |   14 Oct 2026

1

- Day 4 – Doing Scrum – Sprint Simulation

Topics covered: Sprint Planning · Daily Stand-up · Backlog Refinement · Sprint Review and Retrospective · Agile and DevOps Culture · Distributed Teams

- Set 1 – Digital Wallet Application – Mid-Sprint Change

| Business Scenario | A fintech team of five developers is in a 10-day sprint. Previous sprint velocities were 21, 24 and 23 story points. On day 4 the business asks for a refund-to-wallet feature. |
| --- | --- |
| Tasks | 1. Calculate the average velocity, select stories from a supplied backlog to match it, and write a measurable Sprint Goal. 2. Break three selected stories into tasks with hour estimates and record them on the sprint board. 3. Write a daily stand-up update (yesterday, today, impediment) for three team members on day 3. 4. Re-prioritise the backlog after the refund-to-wallet request: state what is added, what is removed and who decides. 5. Prepare a sprint burndown for 10 days from a supplied completed-points table and interpret the trend. 6. Write the retrospective (what went well, what to improve, two action items with owners) and map the Definition of Done to a build pipeline (build, test, review, merge). |
| Deliverables | Sprint backlog, impediment log, burndown chart, retrospective actions and a half-page pipeline mapping. |

- Set 2 – Airline Web Check-in – Blocked Dependency

| Business Scenario | An airline's web check-in team is mid-sprint when the payment-gateway sandbox needed for the seat-upgrade story becomes unavailable. |
| --- | --- |
| Tasks | 1. Compute the team capacity (six members, 8 working days, 70 percent focus factor) and decide the number of points to commit. 2. Write the Sprint Goal and select stories; document the Definition of Ready check for each selected story. 3. Log the impediment (description, impact, owner, escalation path, expected resolution) and show how the Scrum Master would remove it. 4. Run a refinement session on next sprint's top five stories: split one oversized story and re-estimate. 5. Prepare the Sprint Review agenda and demonstration script against the acceptance criteria. 6. Run one stand-up in written, asynchronous format for a distributed team across two time zones and compare it with a live stand-up. |
| Deliverables | Impediment log, sprint plan, review agenda and the written async stand-up. |

- Set 3 – E-Learning Platform – Scope Change Handling

| Business Scenario | An e-learning company's team is on day 6 of a 10-day sprint when the Product Owner asks for a 'certificate download' feature for an upcoming launch. |
| --- | --- |
| Tasks | 1. Using a supplied backlog and velocity of 30 points, plan the sprint and state the Sprint Goal. 2. Analyse the impact of the new request on the sprint: what can be swapped out, what must wait and how the Sprint Goal is protected. 3. Write the stand-up statements for a developer who is blocked on a missing API contract and the Scrum Master's follow-up action. 4. Calculate the velocity for the sprint from a completed-points table where one story is 80 percent done, and explain how partially done work is counted. 5. Facilitate a retrospective using the Start-Stop-Continue format and produce three SMART action items. 6. Explain, in a short note, how automation (unit tests, linting, pipeline) supports the Definition of Done. |
| Deliverables | Sprint plan, change-impact note, velocity calculation and retrospective actions. |

About Hexaware

Hexaware is a global technology and business process services company. Our 28,400 Hexawarians wake up every day with a singular purpose; to create smiles through great people and technology. With this purpose gaining momentum, we are well on our way to realizing our vision of being the most loved digital transformation partner in the world. We also seek to protect the planet and build a better tomorrow for our customers, employees, partners, investors, and the communities in which we operate.

With 45+ offices in 19 countries, we empower enterprises worldwide to realize digital transformation at scale and speed by partnering with them to build, transform, run, and optimize their technology and business processes.

www.Hexaware.com

© 2023 Hexaware Technologies Limited. All rights reserved

Learn more about Hexaware at www.hexaware.com